## WE 1208
Team Member | Roles&responsibilities | Hours worked | Days of work | Tasks completed on time
Jackson Hamill | Manage tasks, (AoA, PMP, Timesheets) | 4.5 | Fri, Sat, Sun | x
Liang Ding | AoA - Architecture | 4 | Fri, Sat | x
Marcus Marinelli | AoA - Programming Language | 4 | Fri, Sat | x
Paul Papadopoulos | Risk Register / Timesheets | 4 | Fri, Sun | x
Richard How | PMP / Risk Register | 4.5 | Fri, Sat, Sun | x
Izad Muhammad Borhan Tan | Risk Register / Timesheets | 4.5 | Fri, Sun | x

## WE 1908
Team Member | Roles&responsibilities | Hours worked | Days of work | Tasks completed on time
Jackson Hamill | Manage tasks, (AoA, PMP, Timesheets) | 2.5 | Fri, Sun | x
Liang Ding | AoA - Architecture | 3 | Mon, Tues, Fri | x
Marcus Marinelli | AoA - Programming Language | 2.5 | Tues, Wed, Fri | x
Paul Papadopoulos | Risk Register / Timesheets | 3 | Thurs, Fri, Sat, Sun | x
Richard How | PMP / Risk Register | 3.5 | Fri, Sat, Sun | x
Izad Muhammad Borhan Tan | Risk Register / Timesheets | 3 | Fri, Sun | x

## WE 2608
Team Member | Roles&responsibilities | Hours worked | Days of work | Tasks completed on time
Jackson Hamill | Review and refine Delieverables / Timesheet Approvals | 2 | Mon, Tues, Fri | x
Liang Ding | Review and refine Delieverables | 1.5 | Mon, Wed, Fri | x
Marcus Marinelli | Review and refine Deliverables | 1.5 | Mon, Wed, Fri | x
Paul Papadopoulos | Review and refine Deliverables / Timesheets | 2 | Mon, Tues, Fri | x
Richard How | Review and refine Deliverables | 1.5 | Mon, Thurs, Fri | x
Izad Muhammad Borhan Tan | Review and refine Deliverables | 2 | Mon, Thurs, Fri | x

## WE 0209
Team Member | Roles&responsibilities | Hours worked | Days of work | tasks completed on time
Jackson Hamill | Sprint Planning Meeting (Contributor) / Timesheets | 2 | Fri | x
Liang Ding | Sprint Planning Meeting (Contributor) / Product Backlog | 1.5 | Fri | x
Marcus Marinelli | Sprint Planning Meeting (Product Owner) / Product Backlog | 1.5 | Fri | x
Paul Papadopoulos | Sprint Planning Meeting (Contributor) / PoC Code | 1.5 | Fri | x
Richard How | Sprint Planning Meeting (Scribe) / API Investigation | 2 | Fri | x
Izad Muhammad Borhan Tan | Sprint Planning Meeting (Contributor) / API Investigation | 2 | Fri | x